## 1.9
| Task plan | 2019-04-11 | 2019-04-12 | 2019-04-13 | 2019-04-14 | 2019-04-15 | 2019-04-16 | 2019-04-17 | 2019-04-18 | 2015-09-19 | 2019-04-20 | 2019-04-21 | 2019-04-22 | 2019-04-23 | 2019-04-24 | 2019-04-25 | 2019-04-26 | 2019-04-27 | 2019-04-28 | 2019-04-29 | 2019-04-30 | 2019-05-01 | 2019-05-02 | 2019-05-03 | 2019-05-04 | 2019-05-05 | 2019-05-06 | 2019-05-07 | 2019-05-06 | 2019-05-06 | 2019-05-07 | 2019-05-08 | 2015-10-08
Role/name | Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
PROJECT Manager (Ben) | Planning project Management , Client contact, get a Team | 8 | 3 | 4 | 6 | 2 | 2 |  | 2 | 2 | 8 | 6 | 2 |  |  | 8 | 8 | 8 | 9 | 8 |  |  | 8 | 8 | 8
Project Manager, Conten devolper(kåre) | Start the project and initial a meeting with goals |  | 8 | 5
Project Manager, Conten devolper and designer(Preben) | Process (identifying plan and project planning) |  |  | 4 | 2
Conten devolper and designer | Research, inspiration |  |  |  | 8 | 2
Project Manager, Conten devolper and designer | Make a plan that are strategic |  |  |  |  | 8 | 4
Content Devolper | Content planning | [5 empty] | 4
Project Manager, Conten devolper and designer | Page Outline and Structure of the Page | [5 empty] | 5 |  | 8 | 8
Task Design
Designer | Make a Style Tiles, Grid and layout | [9 empty] | 6 | 6 | 6
Content Devolper | Devolope the content for the page text etc. | [9 empty] | 8 | 8 | 8
Designer/photo | Get images ready | [9 empty] | 2 | 2 | 2
Task building
Designer | Finish the design and make the wireframes | [14 empty] | 6
Designer and Content Devolper | Do the UX/UI Planning and test them out | [14 empty] | 8 | 8
| UX/UI testing | [21 empty] | 8
Front-end devolper | Code the page and start to integrate Design and Text | [14 empty] | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8
Back-end devolper | Coding and site build. | [14 empty] | 8 | 8 | 8 | 8 | 8 |  |  | 8 | 8
Front-end and Back-end Devolper | Cross test the page on different browser and platform | [22 empty] | 8 | 8
| Validate the code and the page | [23 empty] | 8
Designer, Content Devolper, project Manager and Devolpers | Refinement and fix the last bugs | [24 empty] | 10
| Launch the page | [25 empty] | 8
Floating Task
Project Manager | Recruit Content devolper |  | 3 | 2
| Recruit Designer |  |  | 2 | 2
| Recruit Devolper | [7 empty] | 6 | 6 | 6 | 6 | 6
Project Manager, Conten devolper(kåre) | Staff Meeting |  |  |  |  | 0.10 | 0.10 |  | 0.10 | 0.10 | 0.10 | 0.10 | 0.10
Designer, Content Devolper, project Manager and Devolpers | Staff Meeting | [14 empty] | 0.10 | 0.10 | 0.10 | 0.10 | 0.10 |  |  | 0.10 | 0.10 | 0.10 | 0.10 | 0.10
| Testing | [7 empty] | .15 | .15 | .15 | .15 | .15 |  |  | .15 | .15 | 5 | 5 | 5 |  |  | .15 | 5 | 5 | 5 | 5
| Total Hour on Floating task |  | 3 | 4 | 2 | .10 | .10 |  | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 |  |  | .25 | .25 | .25 | .25 | .25 |  |  | .25 | .25 | .25 | .25 | .25 | [6 empty] | 96
| Total hours on the team | 8 | 11 | 13 | 16 | 12 | 15 |  | 8 | 10 | 24 | 22 | 18 | 0 | 0 | 22 | 16 | 8 | 9 | 8 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56
| Total Hours Days | [6 empty] | Total week 1 | [5 empty] | Total week 2 | . | [5 empty] | Total week 3 | [5 empty] | Total Week 4 |  | total Month
| Procject Man | 8 | 11 | 9 | 8 | 10 | 8 | 54 | 10 | 10 | 8 | 6 | 2 | 36 | . | 8 | 8 | 8 | 8 | 8 | 40 | . | 8 | 8 | 8 | 8 | 40 |  | 158
| Conten devolper | . | 8 | 9 | 10 | 10 | 13 | 50 | 8 | 8 | 8 | 8 | 8 | 40 | . | 8 | 8 | 5 | 5 | 5 | 31 | . | 8 | 5 | 5 | 5 | 23 |  | 144
| designer | . | . | 9 | 10 | 8 | 8 | 35 | 8 | 8 | 8 | 8 | 8 | 40 | . | 6 | 8 | 5 | 5 | 5 | 29 | . | 8 | 8 | . | 10 | 36 |  | 140
| Front-end devolper | . | . | . | . | . | . | . | . | . | . | . | . | . | . | 8 | 8 | 8 | 8 | 8 | 40 | . | 8 | 8 | 8 | 10 | 42 |  | 82
| Back-End devolper | . | . | . | . | . | . | . | . | . | . | . | . | . | . | 8 | 8 | 8 | 8 | 8 | 40 | . | 8 | 8 | 8 | 10 | 42 |  | 82
Days spend on Different tasks
30
28
28
27
26
| 25 | Planning project Management , Client contact
24
23
22
21
20
19
18
17
16
15
14
| 13 |  | get a team
12
11
10
| 9 | [9 empty] | Coding and site build.
| 8 |  |  |  | Get images ready |  | Cross test the page on different browser and platform |  |  |  | Code the page and start to integrate Design and Text
| 7 |  |  |  | Page Outline and Structure of the Page |  | Finish the design and make the wireframes |  | Launch |  |  |  | Do the UX/UI Planning and test them out
| 6 |  |  |  | Process (identifying plan and project planning) |  | Make a plan that are strategic |  | Validate the code and the page |  |  |  | Devolope the content for the page text etc.
| 5 | [5 empty] | Research, inspiration |  | Finish the design and make the wireframes |  |  |  | Make a Style Tiles, Grid and layout
| 4 | [7 empty] | content planning
| 3 | [7 empty] | Refinment and fix bugs
2
1